Strategic Priority 1: Internal Coordination & Communication

Deliverables

- Unified communication policy

- Weekly coordination structure

- Monthly reporting rhythm

- Master activity calendar

Activities

- Draft & approve communication policy (Jan 2026)

- Establish weekly coordination meetings (Feb 2026)

- Introduce shared calendar system (Mar 2026)

- Monthly management meeting framework (Mar 2026)

- Quarterly departmental review sessions (from Q2 2026 onward)

KPIs

- 100% department attendance in monthly review

- Master calendar updated weekly

- Communication policy in effect by Mar 2026

Responsible

- Programme Manager

- HR

- All Department Heads

Strategic Priority 2: Strengthen Governance & SOP Enforcement

Deliverables

- Updated SOP manual

- Compliance checklist

- Finance approval SLA

- Document filing standards

Activities

- SOP Revision Workshop (Jan–Feb 2026)

- Launch compliance monitoring tool (Mar 2026)

- Finance workflow digitalisation (Apr–Aug 2026)

- Document digital archive setup (Q2–Q4 2026)

KPIs

- Reduce approval delays by 70%

- 100% projects follow SOPs in audits

- All departments adopt filing system

Responsible

- HR

- Finance

- MEAL

- Programme Manager

Strategic Priority 3: HR Development & Culture Reform

Deliverables

- Behavioural training framework

- KPIs for all staff

- Leadership development plan

- Performance appraisal system

Activities

- Introduce updated Code of Conduct (Jan 2026)

- Quarterly team behaviour training (from Q1 2026)

- Develop leadership programme (May 2026)

- Implement staff KPIs (Jul 2026)

- Annual appraisal cycle (Dec each year)

KPIs

- 70% reduction in staff conflicts

- 100% staff evaluated annually

- 2 team building events per year

Responsible

- HR

- Country Manager

Strategic Priority 4: Safeguarding & Data Protection

Deliverables

- Child safeguarding framework

- Safeguarding training modules

- Staff–beneficiary communication protocol

- Digital data security

Activities

- Adopt safeguarding policy (Jan 2026)

- Train all staff (Feb–Apr 2026)

- Confidentiality agreements signed (Mar 2026)

- Field safeguarding monitoring checklist (Q2 2026)

- Data security/backup system (Q3–Q4 2026)

KPIs

- Zero safeguarding violations

- 100% staff trained

- Complaint mechanism active

Responsible

- Orphan Care (WOM)

- HR

- MEAL

Strategic Priority 5: Digital Transformation & System Integration

Deliverables

- OMS orphan system fully operational

- HR attendance + KPI system live

- Finance workflow automation

- Cloud document archive

- Dashboard reporting

Activities

- Technical assessment (Jan–Feb 2026)

- Development (Mar–Jul 2026)

- Testing (Aug–Sept 2026)

- Deployment (Oct 2026)

- Optimisation (2027)

KPIs

- 100% orphan files digitised

- 40% reduction in paperwork

- Approval cycle reduced to 5 days

Responsible

- IT/System Developer

- HR

- Finance

- Programme Manager

Strategic Priority 6: Government & Stakeholder Engagement

Deliverables

- Government engagement strategy

- 25+ district meetings

- Government awareness presentations

- Relationship-building framework

Activities

- Send official introductory letters (Jan 2026)

- District-level engagement meetings (Quarterly 2026–2027)

- Annual government partnership workshop (2026 & 2027)

- Maintain approval timeline tracker

KPIs

- 70% reduction in approval delays

- 2 awareness sessions per district per year

Responsible

- Country Manager

- Programme Manager

Strategic Priority 7: Donor Relations, Branding & Public Image

Deliverables

- Branding guideline

- Visibility toolkit

- Crisis communication plan

- Quarterly donor reporting structure

Activities

- Develop branding guideline (Feb 2026)

- Visibility training for staff (Mar 2026)

- Crisis communication SOP (Apr–May 2026)

- Donor reporting calendar (annual)

KPIs

- 100% visibility compliance

- 12 donor communications per year

- 30% increase in donor satisfaction

Responsible

- Media

- Programme Manager

- Funding/Donor Relations Team

3.4 Dependencies & Enablers

Enablers

- Leadership commitment

- Budget availability

- Staff cooperation

- Digital tools

Dependencies

- HQ approvals for system development

- Government cooperation

- Donor timelines

- Training availability

3.5 Monitoring Framework

| Monitoring Tool | Frequency | Owner |
| --- | --- | --- |
| Strategic KPI Dashboard | Monthly | MEAL |
| Department Review | Monthly | PM |
| Steering Committee Review | Quarterly | CM/PM |
| Annual Review | Annually | CM/HQ |